## Лист1
Data | FIO | Task
Planning and project setup
2020-10-20 | Minakov N. & Niyazova D. | Define the task and scope out requirements
2020-10-29 | Niyazova D. | Determine project feasibility
2020-11-01 | Minakov N. | Set up project codebase
Data collection and labeling
2020-11-11 | Niyazova D. | Define ground truth (create labeling documentation)
2020-11-18 | Minakov N. | Build data ingestion pipeline
2020-12-01 | Minakov N. | Validate quality of data
2020-11-28 | Niyazova D. | Revisit Step 1 and ensure data is sufficient for the task
Model exploration
2020-12-15 | Niyazova D. | Establish baselines for model performance
2020-12-31 | Minakov N. | Start with a simple model using initial data pipeline
2021-01-25 | Minakov N. | Overfit simple model to training data
2021-01-05 | Niyazova D. | Stay nimble and try many parallel (isolated) ideas during early stages
2021-02-06 | Minakov N. | Find SoTA model for your problem domain (if available) and reproduce results, then apply to your dataset as a second baseline
2021-02-17 | Minakov N. | Revisit Step 1 and ensure feasibility
2021-02-04 | Niyazova D. | Revisit Step 2 and ensure data quality is sufficient
Model refinement
2021-02-15 | Niyazova D. | Perform model-specific optimizations (ie. hyperparameter tuning)
2021-02-28 | Minakov N. | Iteratively debug model as complexity is added
2021-03-08 | Minakov N. | Perform error analysis to uncover common failure modes
2021-03-08 | Niyazova D. | Revisit Step 2 for targeted data collection of observed failures
Testing and evaluation
2021-03-22 | Minakov N. | Evaluate model on test distribution; understand differences between train and test set distributions (how is “data in the wild” different than what you trained on)
2021-03-22 | Niyazova D. | Revisit model evaluation metric; ensure that this metric drives desirable downstream user behavior
Model deployment
2021-03-30 | Niyazova D. | Expose model via a REST API
2021-03-31 | Minakov N. | Deploy new model to small subset of users to ensure everything goes smoothly, then roll out to all users
2021-04-12 | Niyazova D. | Maintain the ability to roll back model to previous versions
2021-04-05 | Minakov N. | Monitor live data and model prediction distributions
Ongoing model maintenance
2021-04-10 | Niyazova D. | Understand that changes can affect the system in unexpected ways
2021-04-10 | Minakov N. | Periodically retrain model to prevent model staleness
2021-04-21 | Niyazova D. | If there is a transfer in model ownership, educate the new team